## Project Effort
Project Estimation | [8 empty] | Project Schedule
Filled By | TG | Activity | Sub Activity | Simple | Medium | Complex | Effort (In Person Hours) | Effort (In Person Days) | TG2 Developer Allocation | 1
PM | 1 | Requirement Gathering | Requirement Gathering Sessions |  |  |  | 0 |  | TG2 PM Allocation | 1
PM | 2 | Design | Process Design Effort |  |  |  | 0 |  | TG2 Schedule (In Days) | 0
Developer | 2 | Design | Technical Design Effort |  |  |  | 0
|  |  | Sub Total : | 0 | 0 | 0 | 0 | 0 | TG3 Developer Allocation | 1
[9 empty] | TG3 Schedule (In Days) | 0
Developer | 3 | Data Extraction | E-Mail |  |  |  | 0
Developer | 3 | Data Extraction | Data From WebPage |  |  |  | 0 |  | TG4 Developer Allocation | 1
Developer | 3 | Data Extraction | Excel File |  |  |  | 0 |  | TG4 Schedule (In Days) | 0
Developer | 3 | Data Extraction | Oracle ERP |  |  |  | 0
Developer | 3 | Data Extraction | SAP ERP |  |  |  | 0 |  | Operationalization | 0
Developer | 3 | Data Extraction | Database |  |  |  | 0
Developer | 3 | Data Extraction | API |  |  |  | 0 |  | Total Days for Completion | 0
Developer | 3 | Conversion | OCR Image |  |  |  | 0
Developer | 3 | Conversion | XML |  |  |  | 0
Developer | 3 | Conversion | JSON |  |  |  | 0
Developer | 3 | Conversion | Text |  |  |  | 0
Developer | 3 | Data Entry | E-Mail (Generation and Sending) |  |  |  | 0
Developer | 3 | Data Entry | Data To WebPage |  |  |  | 0
Developer | 3 | Data Entry | Excel File |  |  |  | 0
Developer | 3 | Data Entry | Oracle ERP |  |  |  | 0
Developer | 3 | Data Entry | SAP ERP |  |  |  | 0
Developer | 3 | Data Entry | Database |  |  |  | 0
Developer | 3 | Data Entry | API (Researching use of BAPI for SAP operations) |  |  |  | 0
Developer | 3 | File Operation | To/From Box |  |  |  | 0
Developer | 3 | File Operation | To/From FTP |  |  |  | 0
Developer | 3 | File Operation | To/From Library |  |  |  | 0
Developer | 3 | File Operation | Download from WebApp |  |  |  | 0
Developer | 3 | File Operation | Download Oracle ERP Report |  |  |  | 0
Developer | 3 | File Operation | Download SAP ERP Report |  |  |  | 0
Developer | 3 | File Operation | Download BI Report |  |  |  | 0
Developer | 3 | File Operation | File Unzip/Zip |  |  |  | 0
Developer | 3 | Data Processing | Rule Based Decision Points |  |  |  | 0
Developer | 3 | Data Processing | 2 Way Data Table Matching |  |  |  | 0
Developer | 3 | Data Processing | 2 Way Data Table Consolidation |  |  |  | 0
Developer | 3 | Data Processing | Excel Macro |  |  |  | 0
Developer | 3 | Data Processing | Data Table Processing Loop |  |  |  | 0
Developer | 3 | Housekeeping | Queue Structure Building |  |  |  | 0
Developer | 3 | Housekeeping | Process From Queue |  |  |  | 0
Developer | 3 | Housekeeping | Logging |  |  |  | 0
Developer | 3 | Housekeeping | Build Configuration File |  |  |  | 0
Developer | 3 | Housekeeping | Cleanup Activities |  |  |  | 0
Developer | 3 | Housekeeping | Retrieve Assets |  |  |  | 0
Developer | 3 | Project Specific | Setup Library For Storage
|  |  | Sub Total : | 0 | 0 | 0 | 0
Developer | 3 | Code Review Corrections | Code Review Feedback Corrections |  |  |  | 0
PM | 3 | UAT Preparation by PM | Prepare Test Data/ Acceptance Criteria |  |  |  | 0
|  |  | Sub Total : | 0 | 0 | 0 | 0
Developer | 4 | Code Move | Move to Onbording VM |  |  |  | 0
Developer/PM | 4 | UAT | UAT Testing |  |  |  | 0
|  |  | Sub Total : | 0 | 0 | 0 | 0
Admin | Operationalization | Code Move | Move From Onboarding to Production |  |  |  | 0
Developer/PM | Operationalization | Operational Testing | Post Production Validation |  |  |  | 0
|  |  | Sub Total : | 0 | 0 | 0 | 0
|  |  | Grand Total : | 0 | 0 | 0 | 0

## Developer Guide
|  | Simple | Medium | Complex
Data Extraction | E-Mail | Simple text (e.g., "Job Finished" ) | Basic HTML formatting | Variable attachments (maybe one, maybe three, etc); Complex HTML formatting (embedded images, etc)
| Data From WebPage | Simple page structure (well-defined tables, simple text) | More complex text (validation, dropdowns, etc) | HTML5/Angular based pages (dynamic webpages)
| Excel File | Read from a single Sheet | Single sheet structured Data (data required to be in specific places) | ADI templates; Multiple Sheets
| Oracle ERP | Single-screen data; simple text | Multiple selector types, single-screen | off-screen fields; paged data (scrolling, etc)
| SAP ERP | Single-screen data; simple text | Multiple selector types, single-screen | off-screen fields; paged data (scrolling, etc)
| Database | Provided SELECT statement, connection string | Connection provided, no query provided but resources available | No meaningful documentation/support provided
| API | Example provided; authentication a non-issue; REST usually; Simple GETs | Complex REST or simple SOAP; Complex GETs; Simple POSTs | Given end-point, but no documentation/information; Complex SOAP; Complex POSTs
Conversion | OCR Image | Citrix; digital non-scanned text images; PDF (not an image) | Image of PDF (non-scanned) | Scanned documents; Images; Other languages
| XML | Schema is provided | No schema provided (must discover/analyze schema yourself), simple Objects | Nested Objects
| JSON | Schema is provided | No schema provided (must discover/analyze schema yourself), simple Objects | Nested Objects
| Text | Simple list (e.g., single column of names or IDs) | Defined structure (rows being: "key=value" style) | Needs regex parsing; other unstructured text data
Data Entry | E-Mail (Generation and Sending) | Simple text (e.g., "Job Finished" ) | Basic HTML formatting | Variable attachments (maybe one, maybe three, etc); Complex HTML formatting (embedded images, etc)
| Data To WebPage | Search boxes; Logging in | More complex text entry (validation, dropdowns, etc) | HTML5/Angular based pages (dynamic webpages)
| Excel File | Output directly to a single Sheet1 | Structured Data (data required to be in specific places) | ADI templates
| Oracle ERP | Single-screen data entry, simple text entry | Multiple selector types, single-screen | off-screen fields; paged data (scrolling, etc)
| SAP ERP | Single-screen data entry, simple text entry | Multiple selector types, single-screen | off-screen fields; paged data (scrolling, etc)
| Database | Provided insert/update statement, connection string | Connection provided, no query provided but resources available | No meaningful documentation/support provided
| API | Example provided; authentication a non-issue; REST usually; Simple GETs | Complex REST or simple SOAP; Complex GETs; Simple POSTs | Given end-point, but no documentation/information; Complex SOAP; Complex POSTs
File Operation | To/From Box | Use existing Box reusable workflow | Implement one-off Box workflow | Large volume of Files; searching for specific file(s)
| To/From FTP | Use existing UiPath Activity (single file) | Use existing UiPath Activity (multiple files) | Searching for specific file(s)
| To/From Library | Use existing reusable workflow | Implement one-off Library workflow | Large volume of Files; searching for specific file(s)
| Download from WebApp | Direct download link/button | Simple website | Field-entry required prior to download; Searching for specific file(s) (from list, etc)
| Download Oracle ERP Report | Direct download link/button | Simple navigation or simple data entry | Complex Navigation/Data Entry; off-screen links/fields; Building filter
| Download SAP ERP Report | Direct download link/button | Simple navigation or simple data entry | Complex Navigation/Data Entry; off-screen links/fields; Building filter
| Download BI Report | Direct download link/button | Simple navigation or simple data entry | Complex Navigation/Data Entry; off-screen links/fields; Building filter
| File Unzip/Zip | Single file; built-in OS zip functionality | Multiple Files; built-in OS zip functionality | Requires external Zip functionality (e.g., 7zip, gzip, etc)
Data Processing | Rule Based Decision Points | Simple flow control (e.g., If, Case, Do, While) | Complex flow control (many possible cases); Complex Loops (nested loops) | Rule-engine implementation
| 2 Way Data Table Matching | Simple 1:1 relationships | 1:n, or n:1 relationships | n:n; multiple/variable conditions
| 2 Way Data Table Consolidation | Simple 1:1 relationships | 1:n, or n:1 relationships | n:n; multiple/variable conditions
| Excel Macro | Macro provided | Macro not provided; VLOOKUP; moving data; pivot tables | Macro not provided; multiple stages of data manipulation; variable rules
| Data Table Processing Loop | Simple For loop (e.g., enriching/reading values) | Simple Loop, not all rows apply (some conditions) | Multiple decision points/filters/etc.
General | Queue Structure Building
Process From Queue
| Logging | Simple Transaction Based Process | Multistage Process across 5+ workflows | Multistage Process across 10+ workflows
Build Configuration File
| Cleanup Activities | Deleting files; closing applications; closing connections | All simple activities, but against a remote target or multiple locations | Simple activities, but targeted to a specific environment/system, or multiple specific ones
Retrieve Assets

## PM Guide
| Simple | Medium | Complex
Number of process steps | < 5 steps | 5 - 15 steps | >15 steps
Variation (# of scenarios or exceptions) | 1 scenario / exception | 2 - 5 scenarios / exceptions | > 5 scenarios / exceptions
Number of underlying IT systems | 1 to 2 | 3 to 4 | > 4
Clear rules vs human judgement | All rules are codable | Some human judgement | Mainly Human judgement
Structure of data | Structured and Digital data | Mixed data | Unstructured, paper based
Quality of data | High Quality | Variable quality | Low quality
Process standardization | Process fully standardized | Parts of the process are standardized | Process needs to be standardized
Compliance / Security risks | No constraints | Low - Med risk | High risk
Process documentation availability (SOPs, Sample Data, Recordings, etc) | Process documents created and available | Some documents are available | Process documents need to be created
# of distinct screens used in process | 1 to 4 | 5 to 10 | >10
# of output destinations | 1 to 2 | 3 to 4 | >4
Knowledge of SMEs | SMEs are completely aware of the Processes | SMEs need to do some analysis for the process | SMEs are not aware of the Process (they cant be called SMEs then :))

## Estimation Guidelines
Effort Estimates by Activity |  | Simple | Medium | Complex | Non Build Activities |  | Simple | Medium | Complex
Data Extraction | E-Mail | 1 | 5 | 8 | Project Design | Requirment Gathering | 3 | 6 | 9
| Data From WebPage | 2 | 8 | 16 |  | Development Design Effort | 16 | 24 | 32
| Excel File | 1 | 2 | 4 |  | Process Design Effort | 16 | 24 | 32
| Oracle ERP | 4 | 8 | 12
| SAP ERP | 2 | 4 | 6 | Deployment | Move From Onboarding to Production | 3 | 6 | 9
| Database | 1 | 3 | 16 |  | Post Production Validation | 3 | 6 | 9
| API | 2 | 4 | 6
[5 empty] | UAT Testing | Prepare Test Data/ Acceptance | 16 | 24 | 32
Conversion | OCR Image | 2 | 8 | 32 |  | Move to Onbording VM | 12 | 16 | 24
| XML | 1 | 4 | 10 |  | UAT Testing | 40% | 50% | 70%
| JSON | 1 | 3 | 8 |  | Code Review Corrections | 5% | 10% | 15%
| Text | 1 | 2 | 4
Data Entry | E-Mail (Generation and Sending) | 1 | 2 | 6
| Data To WebPage | 2 | 8 | 16
| Excel File | 1 | 2 | 8
| Oracle ERP | 4 | 8 | 16
| SAP ERP | 2 | 4 | 6
| Database | 1 | 3 | 16
| API | 2 | 4 | 6
File Operation | To/From Box | 1 | 2 | 3
| To/From FTP | 1 | 2 | 3
| To/From Library | 1 | 2 | 3
| Download from WebApp | 1 | 2 | 3
| Download Oracle ERP Report | 2 | 4 | 8
| Download SAP ERP Report | 1 | 3 | 6
| Download BI Report | 1 | 3 | 6
| File Unzip/Zip | 1 | 1 | 2
Data Processing | Rule Based Decision Points | 1 | 6 | 16
| 2 Way Data Table Matching | 1 | 3 | 8
| 2 Way Data Table Consolidation | 1 | 3 | 8
| Excel Macro | 2 | 6 | 16
| Data Table Processing Loop | 1 | 3 | 8
General | Queue Structure Building | 1 | 1 | 1
| Process From Queue | 1 | 1 | 1
| Logging | 1 | 3 | 5
| Build Configuration File | 1 | 1 | 1
| Cleanup Activities | 1 | 3 | 5
| Retrieve Assets | 1 | 1 | 1